## Sheet1
Real-time Solar and Wind Energy Forecasting System Project Timeline
| January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
| Week 1 01/01 - 01/08 | Week 2 01/09 - 01/16 | Week 3 01/17 - 01/23 | Week 4 01/24-01/31 | Week 1 02/01 - 02/08 | Week 2 02/09 - 02/15 | Week 3 02/16 - 02/22 | Week 4 02/23 - 02/28 | Week 1 03/01 - 03/08 | Week 2 03/09 - 03/16 | Week 3 03/17 - 03/24 | Week 4 03/24-03/31 | Week 1 04/01 - 04/08 | Week 2 04/09 - 04/15 | Week 3 04/16 - 04/22 | Week 4 04/23-04/30 | Week 1
Data preprocessing (L) | [17 empty] | Key: - S: Simon - L: Lucas - J: Jorge
Code potential models (LS)
Inital implementation of model (LS)
Initial testing using historical data (S)
Integrate API for live weather data for real-time predictions (L)
Prototype Presentation (J)
Stress testing (S)
Refine model (LS)
Test Results Report (L)
Test Results Presentation (S)
Senior Design Night Poster (J)
Senior Design Night (SJ)
Gather feedbak/further refinement (LJ)
Detailed Design Report (S)
Front End Design (J), Hosting (J), Deployment (LS)
Final Design Report (LS)
Final Design Presentation (LJ)
Final Design Poster (SJ)